Attu People and Budget

Players:

Crystal Dushkin President Atka Tribe atkairapresident@gmail.com 907-839-2229

Helena Schmidt President, Attu 501c3 attuanjustice@gmail.com

Bill Billeck Smithsonian Program Mgr. billeckb@si.edu

Steve Delehanty Fish & Wildlife steve\_delehanty@fws.gov

Millie McKeown Aleut Pribilof Islands Ass. Milliem@apiai.org

Rachel Mason NPS Alaska Manager Rachel\_mason@nps.gov

Total of 10 Unangax TBD

Flight: Funding Amount

ANC – Washington DC, RT for two @ 1500 Smithsonian 3000

ANC- Adak, RT for two: Smithsonian 2400

ANC – Adak RT for 8 x !200 Attu 501c3 9600

Boat:

FWS Tigilax Adak - Attu7 days @ $12,894 per day = $90,258 in-kind contribution.

Hotel

Washington DC 2x 2nights @350 Smithsonian 1400

Anchorage 4 nights x2 @200 Smithsonian 1600

Anchorage 4 nights x8 @ 200 Attu 501c3 6400

Stipend 2 days, 2 people DC Smithsonian 400

Stipend 10 days x $100 x 10 persons Attu 501c3 $10000

Anchorage Ceremony

APIA in kind use of Atrium space APIA 1500

APIA Catering for 50 @ $20 each APIA 1000

Russian Orthodox Priest donation APIA 200

TOTAL 2700

Total Smithsonian: $8800 plus transportation costs of remains

Total APIA $2700

Total Attu: $26,400

Total FWS: $90,300

**Total Project: 128,200**

**Potential issues:**

Weather delays likely

Only one flight in/out per week to Adak

 Cancellations may strand members on Adak for 1+ week

 Hotels on Adak?

Agreements with Atka tribe on members going to Smithsonian and to Attu

 Traditional religious/spiritual person

 Camera crew

Raising $26,400 for ten Unangax to go to Adak and Attu

Will the Smithsonian pay for the remains to go to Adak instead of Atka?

APIA buy-in

 Perhaps ask NPS for funding?